## Slide 1
WP5 Demonstrator
Review Meeting
16/01/2014 - Munich

## Slide 2: Overview
Current status of WP 5
Draft proposal of the API
Test Environment description
Result of the meeting with GE in December 2013
Discussion on open tasks
Planning consolidation for 2014

## Slide 3: Main objectives of the WP5 part
Provide a Demonstrator to show the results of the openETCS project (EVC code mainly)
Provide a Test Environment to prepare and run scenarios and produce test reports
Provide a non vital Reference Unit

## Slide 4: Current status of the main tasks (1)
5.1 Functional Specification
  Provided for comments in October 2013
  No comments received
  Then considered as accepted
5.2.A Production of an ON BOARD Simulator Iteration 1
  In progress
  Definition of our API, a draft will be presented

## Slide 5: Current status of the main tasks (2)
5.2.A Production of an ON BOARD Simulator Iteration 1
OBU (PC)
BAL
RAD
ODO
LOOP
CTRL/
CFG
DMI
TIU/
BIU
JRU
STM
Logical interface (TCP / IP)
ERSA EVC Baseline 3
Non formal
API

## Slide 6: Current status of the main tasks (3)
5.2.B Production of an ON BOARD Simulator Iteration 2
  Not started yet
5.3 Production of Test Environment
  Started, related to task 5.2 A
Tasks 5.4 to 5.9
  Not yet started
  Tasks 5.7 to 5.9 : first meeting took place

## Slide 7: API Proposal (1)
The API will allow EVC communicating with the outside world
  Sending and receiving data to and from peripherals:
    From and to (calibration) Odometer
    From and to Train and Brake Interface Unit
    From Balise Transmission Module
    From Loop Transmission Module
    From and to EURORADIO module
    From and to Specific Transmission Module
    From and to Driver Machine Interface
    To Juridical Recording Information
  Additional commands may also be needed to control the EVC (initialisation, status, …)

## Slide 8: API Proposal (2)
Each peripheral will have a simple function set
  For reading data from peripheral
  For writing data to peripheral
  Additional commands to control the peripherals (initialisation, status, error reporting, …)

## Slide 9: Technical details (1)
Protocols, exchanged data formats shall exclusively rely on SRS definitions and format
  Odometer: subset 35 - §12
  TIU and BIU: subset 34
  Balise and Loop: subset 26 - §7 and §8
  Radio: subset 26 - §7 and §8, subset 37 - §7
  STM: subset 35 - §5 and subset 58
  JRU: subset 27 - §4
  DMI: ERSA implementation will be proposed

## Slide 10: Technical details (2)
More complete description is available in a draft documentation which is published on GitHub
  Should be reviewed and improved !
  Could be updated following other WP progress and while implementing
Implementation in C language is ongoing: will match what is currently used in ERSA EVC

## Slide 11: Test Environment (1)
Works are ongoing: bound together at the moment with the ERSA EVC, but will become a standalone application with the result of iteration 1
PC
PC
API
BAL
RADIO
ODO
LOOP
CFG
DMI
TIU
JRU
STM
Scenario controller
Test
results
Logical interface (TCP / IP)
ERSA EVC Baseline 3
PC
BAL
RADIO
ODO
LOOP
CFG
DMI
TIU
JRU
STM
Scenario controller
scenarios
Test
results
ERSA EVC Baseline 3
scenarios

## Slide 12: Test Environment (2)
Can already execute some simple scenarios and is already used internally by ERSA
But will require some work to suit all the requirements:
  Scenario format adaptation
  Test result templates
  …

## Slide 13: Report on meeting with GE (1)
(NON) VITAL
PLATFORM
API
JRU
RAD
ODO
STM
CTRL/
CFG
BALI
TIU/
BIU
DMI
LOOP
ERSA EVC Baseline 3
Non formal
Generated code
Adapter
Train Movement Simulator
national system simul.
Trackside ETCS
simul.
Driver simul.
Physical interface (FFFIS or FIS)
TEST
ENVIRONMENT
(SUBSET 094)

## Slide 14: Report on meeting with GE (2)
GE tasks:
  provision of hardware platform and peripheral on board equipment
  provision of development environment for C language
  provision of wrapper for EVC code integration
  technical support
ERSA tasks:
  integration of EVC code
  interaction with wrapper
  tests
Peripherals and hardware resources
Wrapper
API
EVC

## Slide 15: Open tasks (1)
5.2.B On Board simulator – iteration 2
  Use of generated code provided in WP3
  Proposal :
    Define together priorities for merge of code
    Start with integration of braking curves
    Balise telegram management
    …

## Slide 16: Open tasks (2)
5.3 Production of test environment
  Need to have a template definition for test scenario (defined in 5.4):
  Proposal :
    We can provide to the project our current definition as a starting point
  Need to have a template definition for test report
  Proposal :
    We can provide to the project our current definition as a starting point (log and JRU data)
    More work will be needed

## Slide 17: Open tasks (3)
5.4 Data preparation (DLR leader)
  Track and train data must be provided
  Refine template of test scenario (collaboration with other partners), and test environment if needed
5.6 Data exploitation (DLR leader)
  Refine template of test report (collaboration with other partners), and test environment if needed

## Slide 18: Planning consolidation for 2014
March 2014: First iteration of OBU Simulator
April 2014: Technical discussions with GE
May 2014: Input scenarios
July 2014: Preliminary test Environment
December 2014: WP5 Demonstrator ready (first version with combination of ERSA EVC code and generated code from WP3)

## Slide 19
- Thank you for your attention
- Questions & Answers